## App exchange
AppExchange Launch Checklist | Status
1. Security Review & Compliance
Ensure the app follows Salesforce security guidelines
Use Salesforce Security Scanner to check for security risks
Comply with GDPR, CCPA, and other data privacy regulations | 3- 4 weeks - let me check with venkat and sundar on this
Implement proper authentication & authorization mechanisms
2. Packaging & Metadata Readiness
Package the app properly in a managed package | After test classes - could be taking 2 -3 days after that
Ensure metadata is structured correctly (Objects, Apex classes, Lightning components, etc.) | We are good just need final review
Remove hardcoded values & credentials in the codebase | We are good just need final review
Make sure the app supports Salesforce editions & different org types | We are good just need final review
3. Testing & Performance Optimization
Conduct unit testing (Ensure at least 75% code coverage) | Test classes are reqd and functional testing
Perform UAT (User Acceptance Testing) before submission | Uday's team
Optimize SOQL queries, API calls, and batch processes | In progress - we will discuss in detail
Test the app in different environments (Sandbox, Developer, Production orgs) | We have only one env. -- this could be a challange and not sure how salesforce could take this
4. Documentation & AppExchange Listing
Prepare an Installation Guide for customers
Write a User Guide & Admin Guide for configuration | Zara started working - modify document and add screenshots
Create a Technical Support & Troubleshooting document
Provide a Terms of Service & Privacy Policy
Develop marketing materials (screenshots, videos, demo guides)
5. AppExchange Submission Process
Register as a Salesforce Partner (if not done already)
Submit the app to Salesforce Security Review
Complete Business Approval from Salesforce
Set up a Test Drive & Trial Experience
Publish the app with proper pricing & licensing options

## Timelines
Task | Start Date | End Date |  |  |  | Start Date | End Date
Feature Review with Kapture team | 19th March | 19th March | Feature Review with Kapture team | 19th March | Feature Review with Kapture team | 19th March | 19th March
Feedback Incorporation - Kapture team's feedback | 19th March | 24th March | Feedback Incorporation - Kapture team's feedback | 24th March | Feedback Incorporation - Kapture team's feedback | 19th March | 24th March
First Review with Sandeep - Appexchange | 21st March | 21st March | First Review with Sandeep - Appexchange | 21st March | First Review with Sandeep - Appexchange | 21st March | 21st March
First Review with Shri/Sundar - Appexchange | 21st March | 21st March | First Review with Shri/Sundar - Appexchange | 21s March | First Review with Shri/Sundar - Appexchange | 21st March | 21s March
Demo with Bala | 25th March | 25th March | Demo with Bala | 25th March | Demo with Bala | 25th March | 25th March
Second Review with Sandeep - Appexchange | 26th March | 26th March | Second Review with Sandeep - Appexchange | 26th March | Second Review with Sandeep - Appexchange | 26th March | 26th March
Second Review with Shri/Sundar - Appexchange | 26th March | 26th March | Second Review with Shri/Sundar - App exchange | 26th March | Second Review with Shri/Sundar - App exchange | 26th March | 26th March
Testing & Performance Optimization | 19th March | 5th April | Testing & Performance Optimization - ETA | 28th MArch | Testing & Performance Optimization - ETA | 19th March | 5th April
Security Review & Compliance | 18th March | 20th April | Security Review & Compliance - ETA | 31st MArch | Security Review & Compliance - ETA | 18th March | 20th April
Packaging & Metadata Readiness | 18th March | 10th April | Packaging & Metadata Readiness - ETA | 1st April | Packaging & Metadata Readiness - ETA | 18th March | 10th April
Feedback Incorporation - Bala's feedback | 26th March | 2nd April | Feedback Incorporation - Bala's feedback | 2nd April | Feedback Incorporation - Bala's feedback | 26h March | 2nd April
Documentation & AppExchange Listing | 14th March | 20th April | Documentation & AppExchange Listing - ETA | 3rd April | Documentation & AppExchange Listing - ETA | 14th March | 20th April
Final Review with Sandeep and Sundar | 20th April | 21st April | Final Review with Sandeep and Sundar | 4th April | Final Review with Sandeep and Sundar | 20th April | 21st April
AppExchange Submission Process | 21st April | 25th April | AppExchange Submission Process - ETA | 7th April | AppExchange Submission Process - ETA | 21st April | 25th April
AppExchange Deployment | 25th April | 25th April | App exchange Deployment - ETA | 9th April | App exchange Deployment - ETA | 25th April | 25th April
Task | Start Date | End Date
Feature Review with Kapture team | 19th March | 19th March
Feedback Incorporation - Kapture team's feedback | 19th March | 24th March
Internal Review | 21st March | 21st March
Demo with Bala | 25th March | 25th March
Second Internal Review | 26th March | 26th March
Feedback Incorporation - Bala's feedback | 26th March | 2nd April
Testing & Performance Optimization | 19th March | 30th March
Security Review & Compliance | 18th March | 10th April
Packaging & Metadata Readiness | 18th March | 10th April
Documentation & AppExchange Listing | 14th March | 10th April
AppExchange Submission Process | 10st April | 15th April
AppExchange Deployment | 14th April | 15th April

## Dependencies
Partner portal screen match in our org - we do not have option for listing, project and console |  |  | Salesforce case is created
Test classes creation | 75 % passing from Test factory | All the Apex classes should be cmpliant with test factory
How we can prioritize the case - Increase the turnaround time for the cases which we are creating for support |  |  |  | Discuss with Sandeep and sundar and venkat