## Project Timeline
|  |  | 2025-04-11 | 18 Apr | 25 Apr | 2 May | 9 May | 16 May | 23 May | 30 May
Task |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Integration & APIs - Integration with Additional data sources | Owner | Dependency If any
Creating new forms (Adding 6 Data source) | Zara & Mayur | Need additional dev resource support | bar: 2025-04-11 Week 1 to 25 Apr Week 3
Integrating new APIs | Zara & Mayur | bar: 18 Apr Week 2 to 25 Apr Week 3
Testing New APIs | Zara & Mayur | bar: 25 Apr Week 3 to 2 May Week 4
Pricing Model
Kapture end evaluation for limiting features | Uday & Venkat & Bala | bar: 18 Apr Week 2 to 25 Apr Week 3
Salesforce end evaluation for limiting features | Uday & Venkat & Bala | bar: 2 May Week 4
Decision on Pricing Model | Bala | bar: 9 May Week 5
Additional dev (freemium, if limiting at Kapture) | Uday | Kapture side change only | bar: 9 May Week 5 to 23 May Week 7
Additional dev (freemium, if NOT limiting at Kapture) |  |  | 2025-04-11 Week 1: It will be a new full-fledge project
Design Enhancements
Initial design by Guru | Guru | bar: 2025-04-11 Week 1 to 18 Apr Week 2
Design review with Bala | Guru & Bala | bar: 18 Apr Week 2 to 25 Apr Week 3
Final Design readiness | Guru & Mayur & Zara | bar: 25 Apr Week 3 to 2 May Week 4
Marketing & Documentation
Initial Marketing team collaboration | Shyam | bar: 18 Apr Week 2 to 25 Apr Week 3
AppExchange doc review & submission | Shyam | bar: 18 Apr Week 2 to 23 May Week 7
Test classes clousure
Closure on existing test class clearance | Zara & Mayur | bar: 2025-04-11 Week 1 to 25 Apr Week 3
New test classes and passing | Zara & Mayur | bar: 25 Apr Week 3 to 9 May Week 5
Code Review & Code Scan
Need setup GitHub Branch for code review | Mayur & Zara
Code Review & Code Scan | Mayur & Sri

## Sheet1
Feild | Data type