## Kapture
Application | Flow | Owner | Start Date | Due Date | Effort in Hrs | Status | Comments/Concerns
kAdmin
kAdmin | Setup And Login kAdmin | Swamy | 2021-02-04 | 2021-02-05 | 16 | Completed | Setup- Framework (Include)
kAdmin | kAuthoring Administration - Add New Role | Swamy | 2021-02-08 | 2021-02-08 | 8 | Completed
kAdmin | kSearch Widget Role - Add New Role | Swamy | 2021-02-09 | 2021-02-10 | 10 | Completed
kAdmin | kDictionary Role - Add New Role | Swamy | 2021-02-10 | 2021-02-11 | 10 | Completed
kAdmin | Admin Portal Role - Add New Role | Swamy | 2021-02-11 | 2021-02-12 | 12 | Completed
kAdmin | User Group - Add New User Group | Swamy | 2021-02-15 | 2021-02-15 | 4 | Completed
kAdmin | Teams - Add New Team | Swamy | 2021-02-15 | 2021-02-15 | 4 | Completed
kAdmin | User - Add New User | Swamy | 2021-02-16 | 2021-02-17 | 16 | Completed
kAdmin | Profile Picture and Theams changing | Swamy | 2021-02-18 | 2021-02-18 | 8 | Completed
kAdmin | kAuthoring Administration - Edit Role | Swamy | 2021-03-04 | 2021-03-04 | 4 | Completed
kAdmin | kAuthoring Administration - Delete Role | Swamy | 2021-03-04 | 2021-03-04 | 2 | Completed
kAdmin | kSearch Widget Role - Edit Role | Swamy | 2021-03-04 | 2021-03-04 | 4 |  | Issue to be fixed, already in zoho
kAdmin | kSearch Widget Role - Delete Role | Swamy | 2021-03-05 | 2021-03-05 | 2 | Completed
kAdmin | kDictionary Role - Edit Role | Swamy | 2021-03-05 | 2021-03-05 | 4 | Completed
kAdmin | kDictionary Role - Delete Role | Swamy | 2021-03-05 | 2021-03-05 | 2 |  | Issue to be fixed, already in zoho
kAdmin | Admin Portal Role - Edit Role | Swamy | 2021-03-08 | 2021-03-08 | 4 |  | Issue to be fixed, already in zoho
kAdmin | Admin Portal Role - Delete Role | Swamy | 2021-03-08 | 2021-03-08 | 2 | Completed
kAdmin | User Group - Edit User Group | Swamy | 2021-03-08 | 2021-03-09 | 4 |  | Issue to be fixed, already in zoho
kAdmin | User Group - Delete User Group | Swamy | 2021-03-09 | 2021-03-09 | 2 | Completed
kAdmin | Teams - Edit Team | Swamy | 2021-03-09 | 2021-03-09 | 4 | Completed
kAdmin | Teams - Delete Team | Swamy | 2021-03-10 | 2021-03-10 | 2 |  | Issue to be fixed, already in zoho
kAdmin | User - Edit User | Swamy | 2021-03-10 | 2021-03-10 | 6 | Completed
kAdmin | User - View User | Swamy | 2021-03-10 | 2021-03-10 | 3 | Completed
kAuthoring
kAuthoring | Login - kAuthoring | Swamy | 2021-02-19 | 2021-02-19 | 0 | Completed | Internal Demo on kAdmin
kAuthoring | Category - Create New Category | Swamy | 2021-02-19 | 2021-02-19 | 6 | Completed
kAuthoring | Category - Create Sub Category | Swamy | 2021-02-22 | 2021-02-22 | 4 | Completed
kAuthoring | Work Flow - Create New Work Flow | Swamy | 2021-02-22 | 2021-02-23 | 12 | Completed
kAuthoring | Profile Picture and Theams changing | Swamy | 2021-02-23 | 2021-02-23 | 2 | Completed
kAuthoring | Content Type - Create New Content Type | Swamy | 2021-02-24 | 2021-02-25 | 10 |  | Issue to be fixed, already in zoho
kAuthoring | Article - Create New Article | Swamy | 2021-02-25 | 2021-02-26 | 10 |  | Issue to be fixed, already in zoho
kAuthoring | Category - Delete Category | Swamy | 2021-03-15 | 2021-03-15 | 2 | Completed
kAuthoring | Category - Delete Sub Category | Swamy | 2021-03-15 | 2021-03-15 | 2 | Completed
kAuthoring | Work Flow - Edit Work Flow | Swamy | 2021-03-15 | 2021-03-15 | 2 | Completed
kAuthoring | Work Flow - Delete Work Flow | Swamy | 2021-03-15 | 2021-03-15 | 2 | Completed
kAuthoring | Content Type - Delete Content Type | Swamy | 2021-03-16 | 2021-03-16 | 2 | Completed
kAuthoring | Article - Edit Article | Swamy | 2021-02-26 | 2021-02-26 | 4 |  | Issue to be fixed, already in zoho
kAuthoring | Article - Delete Article | Swamy | 2021-03-16 | 2021-03-16 | 2 | Completed
kAuthoring | Task & Notification | Swamy |  |  |  |  | Issue to be fixed, already in zoho
kAuthoring | Global Variables | Swamy |  |  |  |  | Issue to be fixed, already in zoho
kAuthoring | Global Find | Swamy |  |  |  |  | Issue to be fixed, already in zoho
kAuthoring | Global Find and Replace | Swamy |  |  |  |  | Issue to be fixed, already in zoho
kSearch
kSearch | Login - kSearch | Swamy | 2021-03-01 | 2021-03-01 | 4 | Completed
kSearch | Search related Item and verifying | Swamy | 2021-03-01 | 2021-03-02 | 6 | Completed
kSearch | Adding New Widgets | Swamy | 2021-03-02 | 2021-03-03 | 12 | Completed
kSearch | Profile Picture and Theams Changing | Swamy | 2021-03-03 | 2021-03-03 | 2 | Completed
kSearch | Advanced Search related Item and verifying | Swamy | 2021-03-16 | 2021-03-16 | 4 | Completed
kSearch | Deleting Added Widgets | Swamy | 2021-03-17 | 2021-03-17 | 8 | Completed
kSearch | Verifying Synonyms relating Testing | Swamy | 2021-03-18 | 2021-03-18 | 2 | Completed
kDictionary
kDictionary | Login - kDictionary | Swamy | 2021-03-11 | 2021-03-11 | 2 | Completed
kDictionary | Synonyms - Create Synonyms | Swamy | 2021-03-11 | 2021-03-11 | 3 | Completed
kDictionary | Stop Words - Create Stop Word | Swamy | 2021-03-12 | 2021-03-12 | 3 | Completed
kDictionary | Profile Picture and Theams Changing | Swamy | 2021-03-12 | 2021-03-12 | 2 | Completed
kDictionary | Synonyms - Edit Synonyms | Swamy | 2021-03-18 | 2021-03-18 | 2 | Completed
kDictionary | Synonyms - Delete Synonyms | Swamy | 2021-03-18 | 2021-03-18 | 2 | Completed
kDictionary | Stop Words - Edit Stop Word | Swamy | 2021-03-18 | 2021-03-18 | 2 | Completed
kDictionary | Stop Words - Delete Stop Word | Swamy | 2021-03-19 | 2021-03-19 | 2 | Completed